## Sheet1
KEY
Red = Not to timescale; Amber = In progress; Green = To target; Blank = No action to date
QAA&PM: Quality Assurance, Audit & Performance Management sub-group P&P: Policy & Procedures sub-group T&D: Training & Development sub-group AEC: Awareness, Engagement and Communications sub-group MCA: Mental Capacity Act Practice Development sub-group
Domain 1. Prevention & Early Intervention Outcome 1: a pro-active approach reduced risks and promotes safe services whilst ensuring independence, choice and control
KEY OBJECTIVE | Actions required to address/meets the objective | By When | Lead Agency/Officer | Progress | RAG Score

## All Data
Domain 1. Prevention & Early Intervention . Outcome 1: proactive approach reduces risks and promotes safe services whilst ensuring independence choice and control
Key Objective | Actions required to address / meet the objective | By When | Lead Agency / Officer | Progress | RAG Score
1.1 Assure that information is shared appropriately and in a timely manner within and across partner agencies | A. Review LSAB and single agency information sharing protocols (relate to Trigger Protocol). Identify key areas for information sharing | 12/13 | P&P group / LSAB agencies | Complete (Dec 13: on agenda for LSAB approval; awaiting final version for authorisation in June 14) | G
| B. Carry out multi-agency audits routinely and report gaps and good practice to LSAB to help improve and shape future practice | Quarterly on going | QAAPM group | Complete (Mar 14: new audit tool piloted in Nov 13 and audits carried out) | G
| C. Develop and implement an effective Triggers Protocol (including both Commissioners and Providers triggers) | To be confirmed | P&P group | Dec13: currently awaiting outcome of SCR action plan re MASH before continuing this work Mar 14 and June 14: as above. Sept 14: as above | A
1.2 Ensure Carers needs are supported | A. Implementation and review of Carers Action Plan | 12/12 | AEC group | Complete (June 13: Action plan reviewed in June. Carers Centre updating plan) | G
| B. LSAB partners to support and promote joint working with carers centre | 12/12 | AEC group | Complete (Carers Centre has met with Sirona, Curo and AWP and has begun discussions on how to work more effectively together) | G
1.3 Support service users to identify risks and to reduce and prevent abuse occurring | A. Monitor service user feedback from safeguarding process | 06/13 | AEC group | Complete (Oct 13: Reviewed feedback questionnaires with Sirona and Yoursay and service users edited) | G
| B. Promote through training, development and effective supervision, an ethos of choice and control by achieving the right balance between safeguarding action and proactive risk enablement | 12/12 | T&D group | Mar 14: ‘Joint Thresholds Workshops x2 for Sirona and B&NES Managers facilitated by GW and LH in Jan 14. Positive feedback from senior managers re both events - felt would aid supervision standards | G
| C. Develop further service user feedback opportunities | 09/14 | AEC group | Complete (Dec 13: Agreed and now awaiting Healthwatch to recruit lay members). June 14: Currently no volunteers have come forward. Will need to review if no volunteer comes forward in the next 3 months. Sept 14: no update | A
1.4 Work more closely with the LSCB to ensure areas of cross over are addressed; e.g. Transitions and Mental Health | A. Establishment joint LSAB / LSCB working group | 09/12 | LSCB and LSAB working group | Complete | G
| B. LSCB/LSAB chairs and B&NES Council Strategic Director for People and Communities to make proposals to both Boards | 03/13 | LSAB / LSCB | Complete (Dec 13: work on going) | G
1.5 Assurance that robust lessons learned arrangements are in place (including learning from SCRs, case law and other review documents) | A. Review lessons learned guidance that LSAB agencies and sub groups have in place | 06/13 | QAAPM group | Complete (July 13: agreed with LSAB Chair in Subgroup : No further action required) | G
| B. Draft multi-agency lessons learned guidance | 12/14 | P&P group | Oct/Dec 13: Oct LSAB approved request timescale extended to 12/14 request that it is lined to SCR protocol review due June 2014 and do both by Dec 2014June14: on target for Dec 14 LSAB. Sept 14: as above | A
| C. Ensure recommendations from Winterbourne View and Francis Report are actioned and risks fully understood; ensure included in contract monitoring | 12/12 | QAAPM group | Complete (Oct 13: All providers (RUH, RNHRD, AWP & CCG/ LA presented an update at the Sept QAAPM) | G
NEW Assurance that IMCAs are appropriately used in adult safeguarding | A. Monitor use of IMCAs for Safeguarding cases and report back to the LSAB. (currently use of IMCAs is low for B&NES and we are an outlier regionally) | 09/14 | MCA group | Mar 14: The group is aware of this and is working with Sirona Care and Health, AWP and Council staff to promote the use. SWAN Advocacy – the IMCA provider is also monitoring the applications and referral routes. June 14: work on-going. Sept14: On the agenda for the Sept MCA meeting; will update at Dec LSAB | A
Domain 2. Responsibility & Accountability . Outcome 2: There is a multi-agency approach for people who need safeguarding support
Key Objective | Actions required to address / meet the objective | By When | Lead Agency / Officer | Progress | RAG Score
2.1 Develop and improve links with Clinical Commissioning Groups (CCGS) | A. Provide joint training events for Practice and District Nurses | 12/12 | Sirona Care and Health and CCG | Mar 14: CCG rep developing primary care training strategy for 2014/15 to include joint training opportunities | A
| B. Monitor CCG actions from SCR recommendations and lessons learned | On going | QAAPM group | Complete (Dec 13: Actions for CCG are being implemented) | G
| C. Provide training for independent contractors | 03/13 | Council and CCG | Complete (June 13: Four workshop were provided to independent contractors during quarter 4 2012-13) | G
2.2 Formalise accountability arrangements between the LSAB, commissioner and commissioned services | A. Draft guidance note as required setting out the Commissioner and LSAB responsibilities | 12/12 | Council to draft for LSAB discussion | Dec 12: Initial discussion with LSAB Chair and Dept. People and Communities taken place; P&C leadership team agreed to develop draft for 01/13; timescale of 12/12 will slip until Jan 13 though work is in progress. March 13: Discussion paper presented to the LSAB and workshop planned. June 13: LH and RC finalising details of session on this - considering LSAB Away day. Oct 13: Awayday planned for Nov at which this will be discussed. Dec13: Considered at LSAB awayday and Commissioners to bring paper to LSAB in March 14 in terms of commissioner accountability. Mar 14: paper to LSAB. June 14: LSAB to discuss paper - Complete | G
2.3 LSAB agencies to complete self -assessment annually to demonstrate continuous development. NEW ACTION | A. Identify areas for improvement from partner agencies and LSAB through annual self-assessment and include progress in annual report | 06/12 Now 09/14 | QAAPM group | Mar 14: Updated paper to Feb QAAPM then to LSAB based on feedback from last LSAB – expected Sept 14. June 14: QAAPM has started this work. Sept 14: awaiting updates from LSAB partners on action plans, update to Sept | A
| B. Incorporate areas for improvement into LSAB Business Plan annually | 12/12 Now 09/14 | QAAPM group | Mar 14: areas for business plan to be included once LSAB has approved final report – expected Dec 14 | A
| C. As a follow on from the Feedback questionnaire on the effectiveness of the LSAB it has been agreed that a survey will be undertaken to obtain feedback from LSAB partners and wider groups involved in safeguarding e.g.. Care Forum, Strategic Dom Care Partners on the performance of the LSAB Chair | 06/14 | QAAPM group | June 14: provide outline proposal for undertaking this survey. June14: Discussion at LSAB. No further action required on this project - NOT REQUIRED | G
2.4 Assure sub-groups are meeting strategic objectives of the LSAB | A. Review sub group Terms of Reference | 06/12 | All sub groups | Complete | G
2.5 Assure that learning identified in SA annual reports are addressed | A. Monitoring of progress on addressing action points in annual report 10/11 | 09/12 | QAAPM group | Complete | G
| B. Incorporate and monitor learning from annual reports into Business plan | annual | Council Commissioning Lead | Complete | G
2.6 Assure that Whistle blowing arrangements are robust | A. Whistle blowing statement to be included in revised multi-agency policy | 12/12 | P&P group | Complete (June 13 statement in SA Policy) | G
| B. Review LSAB and sub group agencies whistle blowing policies and procedures and report back to LSAB | 12/12 | QAAPM | Complete (Dec 12) | G
| C. Disseminate Whistle blowing best practice guidance widely | 09/12 | AEC group | Complete (Request for good practice example to balance the bad practice example – to be included when document reviewed) | G
2.7 Assurance that the work of the LSAB is incorporated into contracts and embedded in the work of partner agencies | A. Confirmation of how safeguarding and MCA/DOLS indicators are monitored in commissioned services contracts | 12/12 | Council and CCG Commissioning | Complete | G
| B. Propose mechanisms to improve reporting and monitoring arrangements | 03/14 | Council and CCG Commissioning | Dec 12: Initial conversation taken place about the development of an overarching health and social care assurance framework (including children services for safeguarding) building on adults assurance framework that currently exists. June13: Work is in progress on this. Oct 13: Work is slow and request move timescale to 03/14. Dec13: Meeting scheduled for 9th Dec for commissioners to agree assurance and monitoring arrangement. Mar14: paper presented to LSAB. June 14: See 2.2 above. | G
| C. Monitor implementation of above mechanism | 09/13. New 06/14 | QAAPM group | Mar 14: Meeting held in Dec. Proposal to LSAB in Mar 14. June 14: paper presented to LSAB. June 14: See 2.2 above. July 14: Performance indicators in contract discussed at QAAPM in July | A
| D. Develop / review assurance arrangements regarding MCA practice (5.1 ToR) | 03/14New 12/14 | MCA group | Mar 14: multi-agency task and finish group have met three times but have been unable to develop indicators and assurance. Next step is to look at North Somerset’s assurance model for MCA. June14: on-going. Sept 14: due Dec 14 | A
| E. Propose MCA / DOLS indicators for LSAB | 03/14 New 12/14 | MCA group | June 14: As above. Sept14: due before Dec 14 | A
Domain 3. Access & Involvement Outcome 3: People are aware of what to do if they suspect or experience abuse. Outcome 4. Local practice and the commissioning of services and support are informed by feedback and satisfaction levels of those who have had e4xperience of the safeguarding process
Key Objective | Actions required to address / meet the objective | By When | Lead Agency / Officer | Progress | RAG Score
3.1 Ensure service users and alerters have a positive response from professionals through-out the Safeguarding procedure | A. Monitor and review service user experience questionnaire responses (linked to outcome 1) | 12/12 | AEC group | Completed (June 13) | G
| B. Review audit of ‘front door’ response to safeguarding alerts | 12/12 | Sirona report to QAAPM | Completed (June 13; to be repeated Oct 14) | G
3.2 Assure a systematic approach to providing SA and MCA information/ updates to all people /agencies is in place (disseminating) | A. Develop a calendar of opportunities to routinely and strategically disseminate information for a) citizens. b) providers. c) publications | 12/12 | AEC and MCA group | Mar 14: Draft Strategy is being presented to LSAB in Mar 14; calendar of opportunities is underway. June14: Strategy has been approved by the LSAB and will betaken forward to improve co-ordination of the groups work. Sept 14: in progress | A
3.3 Assure that mechanisms are in place for service user and carers feedback to inform improvements to policy, practice, commissioning and service development (personalised; sharing) | A. Monitor effectiveness of service user feedback questionnaire process and responses | 12/12 | AEC group | Completed (paper to LSAB in June 13) | G
| B. Evidence of continual improvement in response to feedback and involvement of service users (requested from AEC group) | 03/13. New 09/14 | QAAPM group | June 13: report being discussed with LSAB in June 13; QAAPM group to consider report and agree how they will achieve this. Oct13: Discussion at Sept QAAPM. Dec 13: QAAPM member reminded of the recommendation and will take account of these in the next survey. Mar 14: Request change of date for completion to Sept 14 as next service user survey is due June 14 | G
3.4 Service users and carers who have been through the safeguarding process to provide peer and mentoring support to other service users and carers | A. Develop a work programme to progress this objective including reviewing the support available. Consider Advocacy and Adult Safeguarding document from ADASS | 06/15 | AEC group | June 13: Advocacy and Adult Safeguarding document from ADASS was considered at June 13 meeting. will look at the review of current feedback and consider future needs and opportunities. A new IMCA provider is starting and the group will introduce themselves to identify professional support available. Sept14: Not due until 06/15 | A
3.5 Raise awareness of discriminatory abuse | A. Agree awareness raising activities specifically for this type of abuse | 12/13 | AEC group | Mar 14: Additional work is taking place to co-ordinate activity with Avon wide Comms Adult Safeguarding Sub Groups including an Adult Safeguarding Week. June14: Now incorporated into strategy | G
Domain 4: Responding to Abuse & Neglect. Outcome 5: People in need of safeguarding support feel safer and further harm is prevented
Key Objective |  | By When | Lead Agency / Officer | Progress | RAG Score
4.1 Assure that service users and carers where appropriate, are fully involved and participate at every stage of the safeguarding process and robust evidence that best interests decisions are made where necessary and clearly recorded (personalised; sharing) | A. Develop person centred procedures on service user involvement to be available and used by all LSAB partners ensureing servie users and carers are treated with dignity | 09/12 | P&P group | Complete (Dec 12) | G
| B. Implement and monitor guidance | 03/14 | QAAPM group | Complete (Mar 14: Group has asked that the policy is updated in line with revised multi-agency procedures. It was also agreed that as we are already looking at service user involvement as part of each case audit and other audits are carried out, that no additional surveys will be undertaken) | G
| C. Request 15% sample audit of cases undertaken by AWP and Sirona Care and Health include a section on compliance with this and demonstrate it is achieved | 05/13 for report | QAAPM group to consider audit report | Complete (Mar 14: In process of revising the audit tool to include standards that both AWP and Sirona can adhere to) | G
| D. Include this in the Carers Action plan in Domain 1. | 09/12 | AEC group | Complete | G
4.2 Assure that multi-agency policies and procedures are reviewed and best practice guidance is developed (including responses to vulnerable perpetrators) (personalised; sharing) | A. Ensure multi-agency policy and procedure review dates are set and list is reviewed on an annual basis. | 03/13 | P&P group | Complete (June 12) | G
| B. Ensure each multi-agency documents are reviewed on a tri - annual basis | 06/12 – 03/15 | P&P group | June 13: In progress. We have 3 due for review by the end of the year – consent, thresholds and media/comms – need to identify lead reviewers for these. Oct 13: Raise3d at June 13 LSAB in progress. Dec 13: Comms and consent being reviewed by relevant subgroups and threshold by 12/14. Mar 14: policies being reviewed are on the agenda for approval. We would like to ask that policies are reviewed on a tri annual basis unless major changes are needed. Time delay between approval and use means that reviewing quickly with less than 2 year's use. We would like to ask that P&P monitor policy review list but policies are reviewed by appropriate sub group e.g. MCA policy or staff framework. TOR's are due for review by each subgroup and LSAB this year - please inform via LSAB that these have been updated. June14: policies and TORs agreed to be reviewed on a tri-annual basis by Mar LSAB. P&P have updated their TOR. All reviews up to date apart from Comms and Media protocol which is being reviewe4d. The group will notify sub group chairs in a timely manner when a review is due | A
| C. Recommend good practice guidance policies and procedures be written resulting from new information provided nationally, locally from SCRs, quality assurance information from audits and lessons learned information | 06/12 – 03/15 | QAAPM and P&P group | Complete (June 13: QAAPM group routinely do and is now regular agenda item). Mar 14: P&P group - Lessons leaned guidance to be developed. June 14: Policy due to come to Dec LSAB | G
4.3 Ensuring a robust process for the management of large scale investigations | A. Develop large scale investigation guidance and procedures with a clear definition | 03/14 | P &P group | Mar 14: draft written in Dec 13; consultation has been extended request extension to June 14 LSAB. June 14: Agenda item for approval | G
Domain 5: Training and Professional Development. Outcome 6: Staff are aware of policies and procedures, their practice safeguards adults and promotes understanding of harm
Key Objective |  | By When | Lead Agency / Officer | Progress | RAG Score
5.1 Ensure organisational commitment to support the development of safeguarding adults and MCA competence in the workforce | A. Roll out audit to LSAB and sub group agencies, carers organisations and Dom Care partners | 09/12. New 06/14 | T&D group | June 14: 2013-14 Audit tool has been circulated with new framework document to all partnership agencies with best practice responses from 2012-13 audit. Sept 14: awaiting audit returns | G
| B. Review Audit Tool (Multi-agency Staff Development Framework) to include MCA | 09/13. New 06/14 | T&D group | June 14: Audit tool reviewed and included 3 new questions to include questions to review standard of content of each level of training in each partner organisation | G
| C. Report audit findings to LSAB | 12/13. New 06/14 | T&D group | Completed. June 14: Responses to the 2014-14 audit due July 2014. Sept 14: awaiting audit returns | G
| D. Report audit findings to LSAB | 12/13. New 06/14 | T&D group | Mar 14: As per update in section B. June14: As per update in section B | G
| E. Develop requirements for Chief Executives, Elected Members and Board members | 12/13 | T&D group | Mar 14: Option to consider use of MACIE approach by providing event in 2014-15 for safeguarding adults leads from partner agencies. June 14: Option to consider use of MACIE approach by providing event in 2014-15 for safeguarding adult leads from partner agencies. Sept 14: No update | A
5.2 Assure that LSAB training targets are achieved | A. Set up a system for LSAB training target reporting (including MCA, DOLS and SA training) | 06/12 | LSAB | Completed | G
5.3 Ensure safeguarding and risk assessment training is delivered and available to service users and carers | A. Ensure training request is included in Carers Centre service specification | 09/12 | Council Carers Lead Commissioner | Completed | G
| B. Ensure service user training is provided through appropriate agency | 09/12 | Council Commissioner | Complete (Mar 13: Delivery of training is included in LD specification for Your Say and for direct payment users through Shaw Trust; Bath People First have funding to deliver this for all service user groups as well however this is not commissioned against a service spec and the agency is currently reviewing its viability and there may be a future gap) | G
5.4 Assure that training meets LSAB standards and competencies set out in the Staff Development Framework are delivered and that service users and carers are involved in delivery where possible | A. Review training provided by Sirona Care and Health and all LSAB agencies | 12/12 | T&D group | June 14: Standards of training to be reviewed as part of framework audit in 2014. Sept 14: in progress | A
| B. Work with the carers centre and support carers to deliver safeguarding training | 03/14 | T&D group | June 14: Carers centre to deliver one course in 14/15 re safeguarding issues in relation to administration of personal budgets e.g., safer recruitment etc. | A
| C. Work with service user representative to support service users to participate in SA training delivery | To be agreed | T&D group | June 14: Partner organisation to be encouraged to include service users in delivering training as best practice | A
| D. Propose level 4 training in Staff Development framework to LSAB | 03/13 | T&D group | June 14: Se 5.2 E update | A

## Dom 1
Domain 1. Prevention & Early Intervention . Outcome 1: proactive approach reduces risks and promotes safe services whilst ensuring independence choice and control
Key Objective | Actions required to address / meet the objective | By When | Lead Agency / Officer | Progress | RAG Score
1.1 Assure that information is shared appropriately and in a timely manner within and across partner agencies | A. Review LSAB and single agency information sharing protocols (relate to Trigger Protocol). Identify key areas for information sharing | 12/13 | P&P group / LSAB agencies | Complete (Dec 13: on agenda for LSAB approval; awaiting final version for authorisation in June 14) | G
| B. Carry out multi-agency audits routinely and report gaps and good practice to LSAB to help improve and shape future practice | Quarterly on going | QAAPM group | Complete (Mar 14: new audit tool piloted in Nov 13 and audits carried out) | G
| C. Develop and implement an effective Triggers Protocol (including both Commissioners and Providers triggers) | To be confirmed | P&P group | Dec13: currently awaiting outcome of SCR action plan re MASH before continuing this work Mar 14 and June 14: as above. Sept 14: as above. Nov 14 - no change. March 15 - no change - Carry forward into MISH work for 15/16 | A
1.2 Ensure Carers needs are supported | A. Implementation and review of Carers Action Plan | 12/12 | AEC group | Complete (June 13: Action plan reviewed in June. Carers Centre updating plan) | G
| B. LSAB partners to support and promote joint working with carers centre | 12/12 | AEC group | Complete (Carers Centre has met with Sirona, Curo and AWP and has begun discussions on how to work more effectively together) | G
1.3 Support service users to identify risks and to reduce and prevent abuse occurring | A. Monitor service user feedback from safeguarding process | 06/13 | AEC group | Complete (Oct 13: Reviewed feedback questionnaires with Sirona and Yoursay and service users edited) | G
| B. Promote through training, development and effective supervision, an ethos of choice and control by achieving the right balance between safeguarding action and proactive risk enablement | 12/12 | T&D group | Mar 14: ‘Joint Thresholds Workshops x2 for Sirona and B&NES Managers facilitated by GW and LH in Jan 14. Positive feedback from senior managers re both events - felt would aid supervision standards | G
| C. Develop further service user feedback opportunities | 09/14 | AEC group | Complete (Dec 13: Agreed and now awaiting Healthwatch to recruit lay members). June 14: Currently no volunteers have come forward. Will need to review if no volunteer comes forward in the next 3 months. Sept 14: no update. Dec 14: Healthwatch have joined the LSAB as an interim position until Lay Member. Mar 15: No change - need to carry into 15/16 Business plan | A
1.4 Work more closely with the LSCB to ensure areas of cross over are addressed; e.g. Transitions and Mental Health | A. Establishment joint LSAB / LSCB working group | 09/12 | LSCB and LSAB working group | Complete | G
| B. LSCB/LSAB chairs and B&NES Council Strategic Director for People and Communities to make proposals to both Boards | 03/13 | LSAB / LSCB | Complete (Dec 13: work on going) | G
1.5 Assurance that robust lessons learned arrangements are in place (including learning from SCRs, case law and other review documents) | A. Review lessons learned guidance that LSAB agencies and sub groups have in place | 06/13 | QAAPM group | Complete (July 13: agreed with LSAB Chair in Subgroup : No further action required) | G
| B. Draft multi-agency lessons learned guidance | 12/14 | P&P group | Oct/Dec 13: Oct LSAB approved request timescale extended to 12/14 request that it is lined to SCR protocol review due June 2014 and do both by Dec 2014 June14: on target for Dec 14 LSAB. Sept 14: as above. Nov 14 - work is ongoing on this policy, may need to delay until March LSAB. Mar 15 - draft has framework has been discussed and final version to be with LSAB in June 15 - Carry forward to 15/16 | A
| C. Ensure recommendations from Winterbourne View and Francis Report are actioned and risks fully understood; ensure included in contract monitoring | 12/12 | QAAPM group | Complete (Oct 13: All providers (RUH, RNHRD, AWP & CCG/ LA presented an update at the Sept QAAPM) | G
NEW Assurance that IMCAs are appropriately used in adult safeguarding | A. Monitor use of IMCAs for Safeguarding cases and report back to the LSAB. (currently use of IMCAs is low for B&NES and we are an outlier regionally) | 09/14 | MCA group | Mar 14: The group is aware of this and is working with Sirona Care and Health, AWP and Council staff to promote the use. SWAN Advocacy – the IMCA provider is also monitoring the applications and referral routes. June 14: work on-going. Sept14: On the agenda for the Sept MCA meeting; will update at Dec LSAB. Dec 14: lack of assurance pursuing with IMCA service and staff. Mar 15: continue to monitor uptake; involved in the advocacy scoping for the Care Act led by Senior Commissioning and have flexibility to address potential demand - will continue to monitor and keep for 15/16 | A

## Dom 2
Domain 2. Responsibility & Accountability . Outcome 2: There is a multi-agency approach for people who need safeguarding support
Key Objective | Actions required to address / meet the objective | By When | Lead Agency / Officer | Progress | RAG Score
2.1 Develop and improve links with Clinical Commissioning Groups (CCGS) | A. Provide joint training events for Practice and District Nurses | 12/12 | Sirona Care and Health and CCG | Mar 14: CCG rep developing primary care training strategy for 2014/15 to include joint training opportunities JT and DC to give final position to recommend move from work plan | A
| B. Monitor CCG actions from SCR recommendations and lessons learned | On going | QAAPM group | Complete (Dec 13: Actions for CCG are being implemented) | G
| C. Provide training for independent contractors | 03/13 | Council and CCG | Complete (June 13: Four workshop were provided to independent contractors during quarter 4 2012-13) | G
2.2 Formalise accountability arrangements between the LSAB, commissioner and commissioned services | A. Draft guidance note as required setting out the Commissioner and LSAB responsibilities | 12/12 | Council to draft for LSAB discussion | Dec 12: Initial discussion with LSAB Chair and Dept. People and Communities taken place; P&C leadership team agreed to develop draft for 01/13; timescale of 12/12 will slip until Jan 13 though work is in progress. March 13: Discussion paper presented to the LSAB and workshop planned. June 13: LH and RC finalising details of session on this - considering LSAB Away day. Oct 13: Awayday planned for Nov at which this will be discussed. Dec13: Considered at LSAB awayday and Commissioners to bring paper to LSAB in March 14 in terms of commissioner accountability. Mar 14: paper to LSAB. June 14: LSAB to discuss paper - Complete | G
2.3 LSAB agencies to complete self -assessment annually to demonstrate continuous development. NEW ACTION | A. Identify areas for improvement from partner agencies and LSAB through annual self-assessment and include progress in annual report | 06/12 Now 09/14 | QAAPM group | Mar 14: Updated paper to Feb QAAPM then to LSAB based on feedback from last LSAB – expected Sept 14. June 14: QAAPM has started this work. Sept 14: awaiting updates from LSAB partners on action plans, update to Sept; Nov 14 - only 1 response received - KP to re-request updates | A
| B. Incorporate areas for improvement into LSAB Business Plan annually | 12/12 Now 09/14 | QAAPM group | Mar 14: areas for business plan to be included once LSAB has approved final report – expected Dec 14 - REQUIRES UPDATE | A
| C. As a follow on from the Feedback questionnaire on the effectiveness of the LSAB it has been agreed that a survey will be undertaken to obtain feedback from LSAB partners and wider groups involved in safeguarding e.g.. Care Forum, Strategic Dom Care Partners on the performance of the LSAB Chair | 06/14 | QAAPM group | June 14: provide outline proposal for undertaking this survey. June14: Discussion at LSAB. No further action required on this project - NOT REQUIRED | G
2.4 Assure sub-groups are meeting strategic objectives of the LSAB | A. Review sub group Terms of Reference | 06/12 | All sub groups | Complete | G
2.5 Assure that learning identified in SA annual reports are addressed | A. Monitoring of progress on addressing action points in annual report 10/11 | 09/12 | QAAPM group | Complete | G
| B. Incorporate and monitor learning from annual reports into Business plan | annual | Council Commissioning Lead | Complete | G
2.6 Assure that Whistle blowing arrangements are robust | A. Whistle blowing statement to be included in revised multi-agency policy | 12/12 | P&P group | Complete (June 13 statement in SA Policy) | G
| B. Review LSAB and sub group agencies whistle blowing policies and procedures and report back to LSAB | 12/12 | QAAPM | Complete (Dec 12) | G
| C. Disseminate Whistle blowing best practice guidance widely | 09/12 | AEC group | Complete (Request for good practice example to balance the bad practice example – to be included when document reviewed) | G
2.7 Assurance that the work of the LSAB is incorporated into contracts and embedded in the work of partner agencies | A. Confirmation of how safeguarding and MCA/DOLS indicators are monitored in commissioned services contracts | 12/12 | Council and CCG Commissioning | Complete | G
| B. Propose mechanisms to improve reporting and monitoring arrangements | 03/14 | Council and CCG Commissioning | Dec 12: Initial conversation taken place about the development of an overarching health and social care assurance framework (including children services for safeguarding) building on adults assurance framework that currently exists. June13: Work is in progress on this. Oct 13: Work is slow and request move timescale to 03/14. Dec13: Meeting scheduled for 9th Dec for commissioners to agree assurance and monitoring arrangement. Mar14: paper presented to LSAB. June 14: See 2.2 above. | G
| C. Monitor implementation of above mechanism | 09/13. New 06/14 | QAAPM group | Mar 14: Meeting held in Dec. Proposal to LSAB in Mar 14. June 14: paper presented to LSAB. June 14: See 2.2 above. July 14: Performance indicators in contract discussed at QAAPM in July | G
| D. Develop / review assurance arrangements regarding MCA practice (5.1 ToR) | 03/14New 12/14 | MCA group | Mar 14: multi-agency task and finish group have met three times but have been unable to develop indicators and assurance. Next step is to look at North Somerset’s assurance model for MCA. June14: on-going. Dec 14: A new national audit tool has been produced and is being discussed by the MCA group in Dec 14, to be shared with the LSAB in Mar 15. Mar 15: Still in draft form with the Department of Health likely to be early summer - will share as soon as possible | A
| E. Propose MCA / DOLS indicators for LSAB | 03/14 New 12/14 | MCA group | June 14: As above; Dec 14: despite the group spending significant time to develop these beyond the training ones already in place it has not been possible to do so. The national group are considering this. Mar 15 no update from the national group on this to date and no suggested timescale but they are in development | A

## Dom 3
Domain 3. Access & Involvement Outcome 3: People are aware of what to do if they suspect or experience abuse. Outcome 4. Local practice and the commissioning of services and support are informed by feedback and satisfaction levels of those who have had e4xperience of the safeguarding process
Key Objective | Actions required to address / meet the objective | By When | Lead Agency / Officer | Progress | RAG Score
3.1 Ensure service users and alerters have a positive response from professionals through-out the Safeguarding procedure | A. Monitor and review service user experience questionnaire responses (linked to outcome 1) | 12/12 | AEC group | Completed (June 13) | G
| B. Review audit of ‘front door’ response to safeguarding alerts | 12/12 | Sirona report to QAAPM | Completed (June 13; to be repeated Oct 14) | G
3.2 Assure a systematic approach to providing SA and MCA information/ updates to all people /agencies is in place (disseminating) | A. Develop a calendar of opportunities to routinely and strategically disseminate information for a) citizens. b) providers. c) publications | 12/12 | AEC and MCA group | Mar 14: Draft Strategy is being presented to LSAB in Mar 14; calendar of opportunities is underway. June14: Strategy has been approved by the LSAB and will betaken forward to improve co-ordination of the groups work. Dec 14: in progress Mar 15: in progress | A
3.3 Assure that mechanisms are in place for service user and carers feedback to inform improvements to policy, practice, commissioning and service development (personalised; sharing) | A. Monitor effectiveness of service user feedback questionnaire process and responses | 12/12 | AEC group | Completed (paper to LSAB in June 13) | G
| B. Evidence of continual improvement in response to feedback and involvement of service users (requested from AEC group) | 03/13. New 09/14 | QAAPM group | June 13: report being discussed with LSAB in June 13; QAAPM group to consider report and agree how they will achieve this. Oct13: Discussion at Sept QAAPM. Dec 13: QAAPM member reminded of the recommendation and will take account of these in the next survey. Mar 14: Request change of date for completion to Sept 14 as next service user survey is due June 14 | G
3.4 Service users and carers who have been through the safeguarding process to provide peer and mentoring support to other service users and carers | A. Develop a work programme to progress this objective including reviewing the support available. Consider Advocacy and Adult Safeguarding document from ADASS | 06/15 | AEC group | June 13: Advocacy and Adult Safeguarding document from ADASS was considered at June 13 meeting. will look at the review of current feedback and consider future needs and opportunities. A new IMCA provider is starting and the group will introduce themselves to identify professional support available. Sept14: Not due until 06/15. Mar 15: not progressed | A
3.5 Raise awareness of discriminatory abuse | A. Agree awareness raising activities specifically for this type of abuse | 12/13 | AEC group | Mar 14: Additional work is taking place to co-ordinate activity with Avon wide Comms Adult Safeguarding Sub Groups including an Adult Safeguarding Week. June14: Now incorporated into strategy | G

## Dom 4
Domain 4: Responding to Abuse & Neglect. Outcome 5: People in need of safeguarding support feel safer and further harm is prevented
Key Objective |  | By When | Lead Agency / Officer | Progress | RAG Score
4.1 Assure that service users and carers where appropriate, are fully involved and participate at every stage of the safeguarding process and robust evidence that best interests decisions are made where necessary and clearly recorded (personalised; sharing) | A. Develop person centred procedures on service user involvement to be available and used by all LSAB partners ensureing servie users and carers are treated with dignity | 09/12 | P&P group | Complete (Dec 12) | G
| B. Implement and monitor guidance | 03/14 | QAAPM group | Complete (Mar 14: Group has asked that the policy is updated in line with revised multi-agency procedures. It was also agreed that as we are already looking at service user involvement as part of each case audit and other audits are carried out, that no additional surveys will be undertaken) | G
| C. Request 15% sample audit of cases undertaken by AWP and Sirona Care and Health include a section on compliance with this and demonstrate it is achieved | 05/13 for report | QAAPM group to consider audit report | Complete (Mar 14: In process of revising the audit tool to include standards that both AWP and Sirona can adhere to) | G
| D. Include this in the Carers Action plan in Domain 1. | 09/12 | AEC group | Complete | G
4.2 Assure that multi-agency policies and procedures are reviewed and best practice guidance is developed (including responses to vulnerable perpetrators) (personalised; sharing) | A. Ensure multi-agency policy and procedure review dates are set and list is reviewed on an annual basis. | 03/13 | P&P group | Complete (June 12) | G
| B. Ensure each multi-agency documents are reviewed on a tri - annual basis | 06/12 – 03/15 | P&P group | March 2015 - All policy review dates clearly monitored and relevant group updated in timely manner to complete review. LSAB agreed 3 yearly review unless changes in legislation etc require prompter action. All being checked currently re Care Act compliance. prompting could then be administartive and P&P group only used as short-life group for specific projects. | A
| C. Recommend good practice guidance policies and procedures be written resulting from new information provided nationally, locally from SCRs, quality assurance information from audits and lessons learned information | 06/12 – 03/15 | QAAPM and P&P group | Complete (June 13: QAAPM group routinely do and is now regular agenda item). Mar 14: P&P group - Lessons leaned guidance to be developed. June 14: Policy due to come to Dec LSAB | G
4.3 Ensuring a robust process for the management of large scale investigations | A. Develop large scale investigation guidance and procedures with a clear definition | 03/14 | P &P group | Complete. March 2015 - to review by June LSAB to ensure Care Act compliance | A

## Dom 5
Domain 5: Training and Professional Development. Outcome 6: Staff are aware of policies and procedures, their practice safeguards adults and promotes understanding of harm
Key Objective |  | By When | Lead Agency / Officer | Progress | RAG Score
5.1 Ensure organisational commitment to support the development of safeguarding adults and MCA competence in the workforce | A. Roll out audit to LSAB and sub group agencies, carers organisations and Dom Care partners | 09/12. New 06/14 | T&D group | June 14: 2013-14 Audit tool has been circulated with new framework document to all partnership agencies with best practice responses from 2012-13 audit. Sept 14: awaiting audit returns; Dec 14 - complete and on agenda | G
| B. Review Audit Tool (Multi-agency Staff Development Framework) to include MCA | 09/13. New 06/14 | T&D group | June 14: Audit tool reviewed and included 3 new questions to include questions to review standard of content of each level of training in each partner organisation | G
| C. Report audit findings to LSAB | 12/13. New 06/14 | T&D group | Completed. June 14: Responses to the 2014-14 audit due July 2014. Sept 14: awaiting audit returns; November 2014 25 returns-13 from LSAB partner agencies,Domicillary care agencies 5,Voluntary sector 7 | G
| D. Report audit findings to LSAB | 12/13. New 06/14 | T&D group | Mar 14: As per update in section B. June14: As per update in section B; November 2014-audit report to go to next LSAB meeting | G
| E. Develop requirements for Chief Executives, Elected Members and Board members | 12/13 | T&D group | Mar 14: Option to consider use of MACIE approach by providing event in 2014-15 for safeguarding adults leads from partner agencies. June 14: Option to consider use of MACIE approach by providing event in 2014-15 for safeguarding adult leads from partner; agencies. Sept 14: No update; Nov 14: No progress to date March 2015 - working with carers centre to develop format for use with Trustees-could be offered to wide range of organisations | A
5.2 Assure that LSAB training targets are achieved | A. Set up a system for LSAB training target reporting (including MCA, DOLS and SA training) | 06/12 | LSAB | Completed | G
5.3 Ensure safeguarding and risk assessment training is delivered and available to service users and carers | A. Ensure training request is included in Carers Centre service specification | 09/12 | Council Carers Lead Commissioner | Completed | G
| B. Ensure service user training is provided through appropriate agency | 09/12 | Council Commissioner | Complete (Mar 13: Delivery of training is included in LD specification for Your Say and for direct payment users through Shaw Trust; Bath People First have funding to deliver this for all service user groups as well however this is not commissioned against a service spec and the agency is currently reviewing its viability and there may be a future gap) | G
5.4 Assure that training meets LSAB standards and competencies set out in the Staff Development Framework are delivered and that service users and carers are involved in delivery where possible | A. Review training provided by Sirona Care and Health and all LSAB agencies | 12/12 and ongoing | T&D group | June 14: Standards of training to be reviewed as part of framework audit in 2014. Sept 14: in progress March 2015 -LSAB training subgroup to review work plan for 2015-16 to ensure training startegy reflects changes required by Care Act including benchmarking content in all levels of training and developing evaluation methodology | A
| B. Work with the carers centre and support carers to deliver safeguarding training | 03/14 | T&D group | March 2015 -see above | A
| C. Work with service user representative to support service users to participate in SA training delivery | To be agreed | T&D group | June 14: Partner organisation to be encouraged to include service users in delivering training as best practice; Nov 14 Theme of second stakeholders event is making safeguarding personal Mar 15: update required | A
| D. Propose level 4 training in Staff Development framework to LSAB | 03/13 | T&D group | June 14: Se 5.2 E update; Dec 14 REQUIRED UPDATE March 2015 Completed | G