## Sheet1
CITY CENTRE SECURITY
PROJECT TIMELINE AND KEY MILESTONES
YEAR | DATE/ PERIOD | PROJECT MILESTONES | DOCUMENTS
2017 | 2017-04-11 | First meeting with Counter Terrorism Intelligence Unit (CTIU), hosted by then Emergency Management Team Manager - Stephen Bell and included Avon & Somerset Counter Terrorism Security Advisor (CTSA) Peter Naish. This was an initial review of counter terrorism measures for the city centre of Bath following an escaliting pattern of attacks across Europe, specifically - 13 between 2000-2013; 3 in 2014; 8 in 2015; 16 in 2016 and 17 in 2017. It was principally concerned with forthcoming events attracting large crowds, particularly the Christmas Market that year.
| 2017-05-17 | Visit to City of Westminster with key Council colleagues to discuss with their project team the types of Hostile Vehicle Mitigation measures they have put in place and the some of the difficulties they have encountered. Site visit followed.
| April - June | Investigation works to understand design guidance, footfall figures, market products (temporary and permanent), revew city centre constraints and 2016 NaCTSO report, which outlined a number of vulnerabilities.
| 2017-06-15 | Meeting with Police CTSA Peter Naish to present first draft for placement of temporary HVM for the 2017 Christmas market. | See dwg. No. MPRPB01-CM-001 (police comments) and e-mail
| 2017-07-05 | First meeting with security consultants MFD International to consider the scheme for the maket footprint and request for Vehicle Dynamic Assessment (VDA) and recommendations for the provision of rated temporary HVM, together with inidcative costs. This would be used for potential sign-off of the market planning application by the Highways Development Control Team.
| October 2017 - March 2018 | Placement of non-rated bollards in Union St and Stall St to bring the existing bollards up to standard in terms of spacing and improve security.
| September | Consideration of placement of the National Barrier Asset (NBA) as recommended within initial report from MFD and meeting on-site with Police CTSA Peter Naish. | See dwg. No. 5023_P1_SK02_4
| 2017-10-19 | Decision taken by informal cabinet not to make use of the NBA, but instead to use 1000kg blocks strategically placed around the perimeter of the Christmas market footprint. Location details outlined within security plan through Bath Tourism Plus (market promoters). Decision based upon the fact that NBA were not able to provide costs in time, timescales, logistical concerns of installation and impact on cellars/ vaults. Blocks were adjudged to be visual deterrant and similar response to many cities across Europe. | E-mail from SB outlining cabinet decision not to use the National Barrier Asset
| November | Project teams starts to consider interim and permanent solutions to protect the city. This would comprise the further use of concrete blocks, as well as looking at solutions for more permanent protection in the form of rated measures. Discussion start with industry as to what products are available on the market that suit our requirements. | See dwg. Nos. MPRPB01-CM-004 and 005
2018 | January - September | Consideration of the future scheme in relation to footfall for the city centre. Limited work undertaken on the project due to funding and directive to concentrate on the 2018 Highways capital programme. Work also included consideration and meetings with Bath Rec representatives wrt their future ground developement and responsibilities for crowd management in advance and after matches.
| December | Visit to the Motor Industry Research Association (Horiba MIRA)/ attendance at CPNI training and information day.
2019 | January | Project start to gather pace once again and position statement set out by D&P to outline work undertaken to date and next steps. | See position statement document
| February | Paper based on the position statement taken to DDG, which also included scope, funding requirements and proposed delivery mechanism. | See document to Cabinet outling position statement
Visit to Counter Terrorism Expo, London to start understanding markets products once again. It is worth noting that this continues to be fast moving market with new and inovative products arriving frequently.
Further meeting with Bath Rugby in advance of potential further planning application submission in April that year.
Set up and first meeting of the Project Steering Group.
| March - May | Meeting with HVM companies and review undertaken on best products to use for the engineering and operational constraints.
| April | D&P appointed Project Managers for the delivery of the City Centre Security project, for inclusion within the capital programme.
Visit to Cardiff CC and meeting their CCTV Hub, Parking Enforcement and Engineering Teams to discuss their security initiatives and understand equipment used, operation and problems encountered.
Initial discussion with Development Control wrt The Mineral Water Hopital development and relationship with the CCS project.
| 2019-05-14 | Meeting with Police CTSA's Peter Naish/ Joanne Johnson-Taylor to outline re-establishment of the project and to present further proposals on the type of HVM considered, hours of operation and next steps. | See meeting note
| May | Request for further VDA work through security consultants D J Goode based upon our proposals.
| July | Members briefing to set out our proposals. | See members briefing note
| October | Informal Cabinet to update on the project in advance of stakeholder consultation and appointment of Place Studio to udnertake the stateholder consultation.
| November 2019 - February 2020 | Engagement with internal B&NES teams and present project to determine potenial effects on their functions.
2020 | February | Initial consultation with 'trusted' partners - Bath Tourism Plus (then), Bath BID, The Abbey, Bath Preservation Trust.
| March | Update to Emergency Services on the proposals and to determine potential operational issues.
Covid-19 begins and project slows as Council wide contingency planning for the pandemic commences.
| March - June | Continuation of workshops with Planning & Heritage Teams.
| May | Guidance provided by CPNI on the vulnerability of queuing pedestrians and people using greater road space to social distance and suggestions for protective measures.
D&P reuqested to commence planning for protective measures as part of the City Centre Access Restriction for Covid-19 social distancing and business recovery.
| 2020-07-23 | Meeting with CTSA Peter Naish to outline project, its operation and potential use of the NBA through the National Vehicle Threat Mitigation Unit (VTMU)
| 2020-06-14 | City centre access restrictions come into force (no protection measures)
| 2020-08-10 | City centre access restrictions with protection measures installed.
| 2020-08-20 | City centre walkabout with CTSA's Peter Naish and Joanne Johnson-Taylor, who are impressed dn supportive of the temporary scheme and how it operates.
| September | Attention starts to turn back to CCS project as the UK climbs out of initial lockdown and into recovery mode.
Discussion with CTSA Peter Naish about a post-Covid CCS and in particular the operational timings, in advance of stakeholder engagement process.
| September/ October | Re-start discussions with Place Studio consultatnts regarding the stakeholder engagement process.
| November 2020 - January 2021 | Stakeholder engagement process.
| January | Appointment of Atkins to undertake accessability study for all city centre projects.
2021 | February - April | Trial Hole works at all 5 sites proposed to place sliding bollards.
| March - present | Cabinet discussions regarding initial scheme proposals, to strive to determine a balanced solution emerging from the consultation and recommendations contained within the accessability study. Discussions also include CT Police.
| April - present | Consideration of designs taking account trial hole information, available cellar survey information and known location of services. Establishment of intial cost for lowering or diverting service equipment. Sructural consideration of the cellars/ vaults beneath the proposed HVM equipment and inital discussion with structural engineers Rexon Day wrt structural assessment and impact if the HVM is impacted during a terrorist incident.