## Goals and Principles
Bath and North East Somerset Food Equity Action Plan
Goals
1. Everyone living in B&NES can reliably afford and access suitable food to meet their needs for energy, nutrition, and social & cultural connection, with dignity and without resort to emergency food aid.
2. In partnership with broader strategies, the growing, production, packaging, transport, marketing and consumption of that affordable and accessible food will contribute to a thriving local economy and a flourishing biosphere.
Principles
The right to food is respected. "The right to food is a human right. It protects the right of all human beings to live in dignity, free from hunger, food insecurity and malnutrition. The right to food is not about charity, but about ensuring that all people have the capacity to feed themselves in dignity" www.righttofood.org/work-of-jean-ziegler-at-the-un/what-is-the-right-to-food/
Food poverty is recognised as an acute form of poverty and preventive measures must, therefore, be taken to tackle poverty at source
Strategies to reduce food poverty must be sustainable in the longer term and embedded in core practice across all agencies .
Ambition
The council uses all the levers at its disposal to maximum effect to reduce food insecurity. These include but are not exclusive to welfare support, commissioning and procurement, planning and the community infrastructure levy for example

## Systems Governance
Systems, Structures and Governance
Aims | Actions | Achieve by | Lead Agency/ Org | Progress
To develop a long term sustainable model for co-ordination of affordable food work locally | Scope a sustainable structure for the Affordable Food Network to enable joint visioning and sustainable funding opportunities | 2024-03-01 | AFN
Widen remit of the IMG to encourage knowledge and skills share with other sectors eg drugs, homelessness, mental health | Update terms of reference of the group and develop membership from other sectors | 2022-06-01 | IMG
| Embed food equity into the Councils Integrated Health Improvement Strategy | 2023-03-01 | PH
Work strategically to inform local sustainable food policy | Continue to explore joint working between PH and climate emergency & sustainability team on joint objectives |  | PH team
Work strategically to explore ways to address income inequality e.g access to good employment, digital inclusion, living wage, social value policies and the potential of anchor institutions | Work to integrate financial wellbeing within wider determinants of health work across the council e.g through engagement with Economic Development Strategy, social value policy etc. |  | PH with support of FFA partners
Improve public and professional awareness of the FFA and its working groups | Develop a webpage for the FFA | 2022-12-01 | PH
Key
IMG | Income Max Group
PH | Public Health
FFA | Fair Food Alliance
AFN | Affordable Food Network

## Money
Financial Wellbeing
Aims | Actions | Achieve by | Lead Agency/ Org | Progress
Increase uptake of entitlements | Increasing uptake of Free School Meals (FSM) | 2023-03-01 | FSM team/Schools
| Promotion of Healthy Start Scheme and new digital offer to increase uptake amongst eligible families | 2023-03-01 | Healthy Start Project Group
| Promotion of pension credit entitlements |  | Age UK / IMG
Co-ordination of crisis support funding and access locally | Scope out feasibility of a 'single point of access' approach to applying for crisis support locally | 2024-03-01 | Council Welfare Support Team & St Johns Foundation
Mainstream financial support and guidance, alongside awareness of food insecurity, within other frontline services | Develop a training package, building in exisitng resources used by IMG and AFN members, to support induction and staff awareness of early identification and support available | 2022-11-01 | IMG/AFN
| Review learning from Poverty Proofing Schools audit tool pilot, embed learning into Public Health schools programme and promote to all schools. | 2022-10-01 | PH - Schools
| Coordinate print and distribution of B&NES Cash First leaflet to support agencies and other community touch points, including a launch event. | 2022-05-01 | PH
Move from signposting to direct referral to strengthen support offer | Explore ways in which services /organisations can move from signposting to direct referral, building on the learning from the community wellbeing hub model | 2024-03-01 | CA
Promotion of safe and secure borrowing and saving options | Work with GWCU to promote Credit Union, improve membership numbers in B&NES and monitor engagement across B&NES area | 2024-03-01 | IMG
| Support awareness campaigns on illegal lending and scamming | 2023-03-01 | IMG
Key
IMG | Income Max Group
PH | Public Health
FFA | Fair Food Alliance
CA | Citizens Advice
FSM | Free School Meal
GWCU | Great Western Credit Union
AFN | Affordable Food Network

## Food
Affordable Food
Aims | Actions | Achieve by | Lead Agency/ Org | Progress
Improve community access to equipment for food storage/prep and cooking | Scope out community resources that support affordable food storage/prep and cooking in the community | 2022-11-01 | AFN
Develop locality food hubs and networks with integral wraparound support | Review learning from the Pathways from Poverty pilot programme and make recommendations for a local model and funding options | 2023-03-01 | CA/Clean Slate
| Include opportunities for education and experience of food growing / preparation/sharing within existing community provision where possible | 2023-03-01 | AFN
| Develop a model of community food hubs and networks for B&NES | 2023-06-01 | AFN / PH
Strengthen action on nutrition advice and cooking skills | Respond to recommendations from children's and adults' weight management pathway review to inform ongoing cooking skills service delivery | 2023-03-01 | PH
Key
IMG | Income Max Group
PH | Public Health
FFA | Fair Food Alliance
CA | Citizens Advice
FSM | Free School Meal
GWCU | Great Western Credit Union
AFN | Affordable Food Network

## Inclusion
Dignity and Inclusion
Aims | Actions | Achieve by | Lead Agency/ Org | Progress
Continue to build local knowledge of need and involvement of those with lived experience | Review report on research findings from University of Bath and incorporate recommendations into FFA action plan as appropriate. | 2022-06-01 | PH
| Use research findings to develop a resource for local agencies to inform further work on community engagement. | 2022-09-01 | PH
| Disseminate research and consultation findings to internal and external stakeholders to inform other partnership strategies. | 2022-09-01 | PH
| Working with Fare Share SW and the Affordable Food Network improve equalities data relating to those accessing food projects | 2022-09-01 | PH
Increase focus on older people – understanding need/barriers to access | Use existing or newly formed networks to raise awareness of support in the community for older people experiencing food insecurity |  | PH
Continue to work on reducing stigma associated with accessing support | Promotion of culturally sensitive and nutritionally balanced and accessible food provision via food banks/clubs/pantries |  | AFN
| Work with AFN members and 3SG to offer Dignity in Practice training and practice development workshops |  | AFN/ 3SG
| Proactive engagement of agencies working with marginalised and vulnerable groups, BAME communities and those with disabilities. |  | AFN/IMG
| Work to understand and raise awareness of support offered around digital inclusion |  | FFA
Better understand needs of 18-24 yr olds living away from home | Work with providers of young people's supported housing to understand experience of food insecurity amongst client group |  | FFA
Key
IMG | Income Max Group
PH | Public Health
FFA | Fair Food Alliance
CA | Citizens Advice
FSM | Free School Meal
GWCU | Great Western Credit Union
3SG | Third Sector Group
AFN | Affordable Food Network